## Book
MOS 2016 Study Guide for Microsoft Excel
| Currently tracking È |  |  | Original content | PM/CE1/Keystroke | AU Doc Review | CE2 | TR | Process Gfx | Layout 1 | Index | Proof 1/Cold Read | AU PDF Review | Gfx Cx as reqd | Layout2 | Proof2 | Final Layout | Proof Cx/Page Turning | Final Index Pass | Final PDFs/eBook | Electronic delivery | Styled Word docs
| #REF! | Doc Pages | PDF Pages | Joan | Kathy | Joan | Kathy | Joan | Jeanne | Susie | Susie | Jaime | Joan | Jeanne | Susie | Jaime | Susie | Kathy | Susie | Susie | Jaime | TBD
a01 | Title | 1 | 1 | [6 empty] | 2016-09-12 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
a02 | LoC/copyright | 1 | 1 | [6 empty] | 2016-09-12 |  | #REF! | #REF! | #REF! | #REF! | #REF!
a03 | Contents | 4 | 4 | [6 empty] | 2016-09-12 |  | #REF! | #REF! | #REF! | #REF! | #REF!
a04 | Introduction | 6 | 6 | 2016-09-10 |  |  |  |  | 2016-09-11 | 2016-09-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
a05 | Taking a Microsoft Office Specialist Exam | 4 | 4 | 2016-09-10 |  |  |  |  | 2016-09-11 | 2016-09-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | Exam 77-727 Microsoft Excel 2016 | 4 | 4 | 2016-09-10 |  |  |  |  | 2016-09-11 | 2016-09-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | Create and manage worksheets and workbooks | 40 | 40 | 2016-09-14 | 2016-08-03 | #REF! | 2016-08-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Manage data cells and ranges | 30 | 30 | 2016-09-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Create and manage tables | 26 | 26 | 2016-09-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | Perform operations with formulas and functions | 26 | 26 | 2016-09-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Create charts and objects | 26 | 26 | 2016-09-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
z01 | Index |  | 6.08 | [11 empty] | #REF! | #REF!
z02 | About the author | 1 | 1 | 2016-09-10 |  |  |  |  | 2016-09-11 | 2016-09-12 |  | #REF! | #REF! | #REF! | #REF! | #REF!
z03 | Survey page |  | 1 | [6 empty] | 2016-09-13 |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | 169 | 176.08 | Sigs: | 11
| Legend |  |  | Over/under target: |  | -0.08
| Not Required |  | 176 | Target
| Complete |  | 224 | Max
| In Progress |  | 160 | Min
Formulas:
Proof 1/Cold Read = WORKDAY([Layout 1],#REF!,holidays)
Proof 1/Cold Read = WORKDAY([Index],#REF!,holidays)
AU PDF Review = WORKDAY([Proof 1/Cold Read],#REF!,holidays)
Gfx Cx as reqd = WORKDAY([AU PDF Review],#REF!,holidays)
Final Layout = WORKDAY(MAX([Layout2]:P14),#REF!, holidays)
Proof Cx/Page Turning = WORKDAY([Final Layout],#REF!,holidays)
Final Index Pass = WORKDAY([Proof Cx/Page Turning],#REF!,holidays)
Final PDFs/eBook = WORKDAY([Final Index Pass],#REF!,holidays)
Electronic delivery = WORKDAY([Final PDFs/eBook],#REF!,holidays)
Styled Word docs = WORKDAY([Electronic delivery],#REF!,holidays)
Index = WORKDAY([Layout 1],#REF!,holidays)
Layout2 = WORKDAY([Gfx Cx as reqd],#REF!,holidays)
Proof2 = WORKDAY([Layout2],#REF!,holidays)
AU Doc Review = WORKDAY([PM/CE1/Keystroke],#REF!,holidays)
TR = WORKDAY([CE2],#REF!)
Process Gfx = WORKDAY([CE2],#REF!,holidays)
Layout 1 = WORKDAY([Process Gfx],#REF!,holidays)
PM/CE1/Keystroke = WORKDAY([Original content],#REF!,holidays)
CE2 = WORKDAY([AU Doc Review],#REF!,holidays)

## Data
Start date | 2016-02-22 | Resource Key | Series Variables
|  |  | Per-Word page | 1
OTSI Non-Working Days |  | Author | Per-graphic | 0
New Year's Day | 2016-01-01 | TR
Memorial Day | 2016-05-30 | CE | Chapter | Word | Gfx | Actual | Projected | Variance
Independence Day | 2016-07-04 | Index | 1
Labor Day | 2016-09-05 | Prod | 2
Thanksgiving | 2016-11-24 | Graphix | 3
Thanksgiving Friday | 2016-11-25 | Proof | 4
Christmas Eve | 2016-12-24 |  | 5
Christmas Day | 2016-12-25 | Page Turn TBD | 6
Boxing Day | 2016-12-26 |  | 7
New Year's Day | 2017-01-01 |  | 8
9
10
Vacations |  |  | 11
12
13
14

## Post-Handoff components (hidden)
Post-Handoff deliverables
eBook
Companion CD
Sample Chapters

## SalesFmt
Person | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Year
Allen | 7222 | 3878 | 5369 | 2763 | 8491 | 5009 | 3956 | 6595 | 8224 | 2790 | 4279 | 8598 | 67174
Grace | 6979 | 5915 | 6102 | 1838 | 1646 | 6619 | 1770 | 6019 | 2291 | 4336 | 5597 | 2315 | 51427
Heather | 1930 | 1602 | 7400 | 6446 | 4457 | 6027 | 5710 | 7951 | 7267 | 6715 | 3268 | 5920 | 64693
Joan | 5656 | 4168 | 2502 | 7927 | 7528 | 3158 | 5439 | 6948 | 8360 | 7132 | 5892 | 4309 | 69019
Linda | 5311 | 7380 | 1897 | 5736 | 7267 | 5505 | 6464 | 6584 | 3426 | 6870 | 5171 | 7562 | 69173
Nancy | 5261 | 4742 | 7706 | 4557 | 4627 | 8021 | 8391 | 7759 | 2969 | 3053 | 5625 | 8644 | 71355
Raina | 7690 | 5318 | 2905 | 8582 | 5654 | 6927 | 4403 | 6290 | 7362 | 7250 | 6873 | 5454 | 74708
Trinity | 8544 | 7295 | 2119 | 6744 | 7220 | 4523 | 3018 | 6971 | 2172 | 5860 | 3045 | 5987 | 63498
Ulrike | 3950 | 6019 | 6678 | 4234 | 4794 | 1800 | 3175 | 7352 | 6075 | 2349 | 4575 | 2291 | 53292
Average | 5838.1111 | 5146.3333 | 4742 | 5425.2222 | 5742.6667 | 5287.6667 | 4702.8889 | 6941 | 5349.5556 | 5150.5556 | 4925 | 5675.5556
Note:
Data includes only sales by full-time salespeople employed the entire year
View as Chart
Next Year
Previous Year